## Discovery deliverables
Discovery Phase — Completion Summary ¦ Merrakii
Prepared by: Maple AI Technologies |  |  |  | Prepared for: Merrakii |  | Issue date: 13 May 2026
Table row | Category | Deliverable | Bundle / notes | What was produced & acceptance note | Value / outcome (per acceptance point) | Status
1 |  | Project kick-off & governance | Measurable: operating model for the engagement is on record | Formal kick-off session held with Merrakii and Maple AI Technologies. | Kick-off session completed on 22nd April 2026. | Complete
|  |  |  | Recurring review cadence defined (frequency, attendees, purpose). | Weekly cadence set up to meet at Merrakii office on Wednesday and Friday.
|  |  |  | Project POCs identified on client (Merrakii) and vendor (Maple AI Technologies) sides. | Ruchii Suri — POC on Merrakii side; Tarun Rastogi — POC on Maple AI Technologies side.
2 | Category A | Brand presentation & business clarity | Website colour theme captured; business purpose captured; business intent captured. | Website colour theme (primary, secondary, accent and usage notes) reviewed with Merrakii and accepted as the baseline for design. | #FFFFEE #C22C31 #01D87 | Complete
|  |  |  | Business purpose for the Merrakii website articulated by stakeholders and confirmed as accurate. | Academic marketplace for the students to search for test preparation courses, certification courses and diploma courses offered by Merrakii's partner vendors, select and apply for the suitable program, pay fees to confirm the enrollment and view their dashboard for historic transactions and incomplete sessions.
|  |  |  | Business intent (what Merrakii expects the website to achieve) documented and agreed with stakeholders. | Attract the users, encourage and guide them to complete the journey to enrollment, clarify and help users with any and all vendors/courses/enrollment related concerns and issues.
3 | Category A | Site pages, services & functional categories | Pages of the website; services to be offered; functional categories — all identified and agreed. | Required pages for launch (and purpose of each) listed and mutually agreed with Merrakii. | HomePage Vendor Catalogue Page Vendor Page Course Page Exam Page Apply Page Payment Page User Dashboard Homepage Transaction Detail Page Internal Dashboard Add Vendor Update Vendor | Complete
|  |  |  | Services Merrakii will present on the website enumerated and validated with stakeholders. | Search by course Search by Vendor Vendor Listing Apply for course Pay for course using payment gateway authorized payment methods Contact Merrakii Provide Merrakii About Us Resume Incomplete Journey View enrolled courses
|  |  |  | Functional categories for the product experience (e.g. discovery, applications, accounts, payments) named and agreed. | Test Preparation Courses Certification Courses Diploma Courses
4 | Category A | Client-authored website content | Website content the client must provide — collected (requirements listed; supplied assets received or logged). | Copy, imagery, institute/service material and other Merrakii-supplied content requirements listed; supplied items received or logged. | Vendor details Vendor Course details Contact Details Terms and Conditions Privacy Policy About Us content Why choose Merrakii content Vendor Testimonials, if any Student Testimonials, if any Blogs, if any | Complete
5 | Category B | Integrations, infrastructure & commercial | Integrations; DNS; payment gateway artefacts; roadmap (Maple AI Technologies); quotation. | Required integrations (e.g. CRM, email capture, analytics, payments) identified with Merrakii and agreed in principle. | OTP integration Email integration Payment Gateway integration | Complete
|  |  |  | Domain registrar/DNS details needed for deployment and cutover gathered from Merrakii or agreed access path. | merrakii.co.in
|  |  |  | Payment gateway vendor forms/checklists issued to Merrakii; completed artefacts received back as required for onboarding. | RazorPay UPI Cards Netbanking EMI Wallets Pay Later
|  |  |  | Phased delivery roadmap (design → build → QA → launch → hypercare or equivalent) presented by Maple AI Technologies and understood by Merrakii. | https://tarun-rastogi.github.io/academic-intelligent-marketplace/digi.html
|  |  |  | Commercial quotation for agreed Discovery outcomes and subsequent phases shared with Merrakii and mutually accepted. | https://tarun-rastogi.github.io/academic-intelligent-marketplace/quotation-academic-intelligent-marketplace-inr.html